## Cover
The name of the institution should be recorded in the XXX below
Bela-Bela Local Municipality
The Example below should be replaced with Draft, Final etc
Risk Register
The date of the workshop should be recorded in the row below
As at: 11 June 2018
Note: The information recorded in the blue lettering above will automatically be recorded on each page of the risk register
In addition the name of the file and the date will also be recorded on each page
To be able to print the entire risk register the sheets need to be grouped together
This is done by clicking on the cover sheet and holding in the shift button and clicking on the How to use sheet simultaneously
The workbook will now reflect that it has been grouped. You can then print in the risk register
It is however important to note that no value should be entered when in the grouped status. On completion of the printing ungroup the sheets and then close the risk register

## Index
Bela-Bela Local Municipality
Risk Register
As at: 11 June 2018
1 | Risk register
2 | Workshop logistics
3 | Categories
4 | Inherent versus residual risk graph
5 | Heatmaps

## Risk register
Bela-Bela Local Municipality
Risk Register
As at: 11 June 2018
2018/2019 STRATEGIC RISK REGISTER
No | Link to objective | Risk category | Risk description | Background to the risk | Risk Refer# | Impact |  | Likelihood |  | Inherent risk |  | Current controls | Perceived control design |  | Residual risk |  | Risk owner | Actions to improve management of the risk | Action owner | Time scale
This column is the risk number | This column should be completed to ensure that the identified risk is linked to the approved strategic plan of the institution | This column should be referenced to the approved risk categories utilised by the institution | This column is to record the identified risk threatening the achievement of the institution's strategic plan | This column should be utilised to capture any additional information needed to contextualise the identified risk |  | The drop down menu should be utilised to record the impact the risk would have on the achievement of the institution's strategic objectives | This column records the numeric value of the impact and is automatic | The drop down menu should be utilised to record the likelihood of the risk occurring within a given timeframe in the absence of controls | This column records the numeric value of the likelihood and is automatic | This is the inherent risk category of each identified risk and is automatically calculated | This column is the inherent risk value of each identified risk and is automatically calculated | This column should be utilised to capture all high level controls implemented by the institution to mitigate the identified risk It should reflect actual controls in place at a given date | The drop down menu should be utilised to record the perceived control effectiveness of each identified risk as ranked by the workshop participants | This column records the numeric value of the perceived control effectiveness | This is the residual risk category of each identified risk and is automatically calculated | This column is the residual risk value of each identified risk and is automatically calculated | The employee that will be responsible for reporting on the movement of the identified risk going forwards will be reflected in this column | This column should be utilised to develop any additional actions that need to be implemented to improve the control effectiveness Care should be taken to ensure that the actions are realistic and not a wish list | For every action a action owner needs to be identified | For every action a time scale needs to be provided Care should be taken to ensure that time scales are realistic and factor into consideration any external influences For example to develop, approve and implement could have a number of time scales
1 | Resource Management of Infrustructure and Services |  | Inability to reduce service delivery backlog - | Higher demand due to influx and pressure to formalise the informal settlement - Limited funding to upgrade electricity,water and sanitation infrastructure to cater increase in population | SR01 | Critical | 5 | Common | 5 | Maximum | 25 | _Reactive mainatence - Implementation of MWIG projects . -Drilling of boreholes of new boreholes and equipping | Satisfactory | 0.65 | Maximum | 16.25 | Municipal Manager | _Implementation of funded electrical projects from DME by 3 phases -Raising for more funding for eletricity projects from other sources - Application for funding to upgrade waste water treatment works -Action to formalise informal settlement | Manager-Technical services | Quartely
2 |  |  | Aging infrastructure | The roads infrastructure was constructed more than 20 years ago, thus lead to increased number of potholes on the road | SR02 | Critical | 5 | Likely | 4 | High | 20 | _Reactive maintenance -Rehabilitation of roads -Rejuveniation of roads | Satisfactory | 0.65 | Maximum | 13 | Municipal Manager | Paving of Extention 4,6& 8 -Upgrading of road Rapotokwane - Replace AC pipes and valves - | Manager-Technical services | on-going
3 | To improve administrative and governace capacity |  | Turn-around time in filling key position | Critical and strategic positions being vacant for the period of more than a year | SR03 | Critical | 5 | Common | 5 | Maximum | 25 | Human Resource Policy . | Satisfactory | 0.65 | Maximum | 16.25 | Municipal Manager | Implementation Human Resource Policy | Acting Manager Corporate Services | on-going
4 |  |  | Public protests | 1.The public protect are most of the time ,caused by the misunderstanding or lack of information. 2.Lack of awareness programmes that could cautiontaze vulnerable groups about municipal programs. | SR04 | Major | 4 | Common | 5 | Maximum | 20 | Mayoral Roadshows with concerned groups at affected wards | Satisfactory | 0.65 | maximum | 13 | Municipal Manager | Continous ward meeting by Mayor and Ward Councillors | Divisional Manager-Communications | Quartely
5 | Promote welfare of community |  | Illegal dumping of waste | Lack of environmental conscience | SR05 | Major | 4 | Likely | 4 | Maximum | 16 | Waste management by-law | Satisfactory | 0.65 | Maximum | 10.4 | Municipal Manager | Conduct environmental awareness campaigns. -Change from 85litre Rubbishbin to 240 Litre | Acting Manager -Social and Community services | Quartely
6 |  |  | Fraud and corruption | _Allegations of fraud -Cases | SR06 | Major | 3 | Likely | 3 | high | 9 | Anti-corruption and Fraud Policy | Satisfactory | 0.65 | medium | 5.85 | Municipal Manager | Anti-fraud and corruption awareness campaing | Chief Risk Officer | "30 March 2018
7 | Financial viability |  | Non compliance with law and regulations | _Auditor General and Internal Audit findings on non-compliance -Low score in Financial Management Competence assessment by Treasury | SR07 | Critical | 5 | Moderate | 3 | Maximum | 20 | _Internal Audit Plan and AG Audit - Financial Management Competence model | Very good | 0.2 | Low | 4 | Municipal Manager | _Auditor General and Internal Audit Action plan -FMC Action plan | All Departmetal Managers | on-going
8 |  |  | Cashflow constraints | -Inability to reach key financial targets. -Inability to meet short term obligations. | SR08 | Critical | 5 | Likely | 4 | Maximum | 20 | -Draft Revenue enhancement strategy -Monitoring of cashflow projections and payment schedule | Weak | 0.8 | Maximum | 16 | Municipal Manager | -Implementing Revenue enhancement strategy after approval - payment register -implementation of MFMA Circular 82 on cost containment measures | Chief Financial Officer | on-going
9 |  |  | Material mistatements in the Annual Financial Statements | Material audit findings raised by AGSA that may lead to negative audit opinion | SR09 | Critical | 5 | Likely | 4 | Maximum | 20 | Management is continously monitoring the implementation of AGs action plan Monitoring of financial internal controls to keep the systems up to date | Very good | 0.2 | low | 4 | Municipal Manager | Compilation of quarterly Financial Statements -Conducting of AFS interim audit | Chief Financial Officer | Quartely
10 | Plan for the future |  | Lack of development and growth | Unable to create environment that is conducive for economic growth | SR10 | Critical | 5 | Common | 5 | Maximum | 20 | outdated LED strategy | Weak | 0.8 | Maximum | 16 | Municipal Manager | Review of LED strategy | Manager Planning and Economic Development | on-going
11 |  |  | inability to implement M-SCOA | Inability to comply with deadline of 1st July 2017 for conversion to M-SCOA | SR11 | Major | 4 | Likely | 4 | Maximum | 20 | _M-SCOA project plan -Meetings of M-SCOA committee to track progress | Satisfactory | 0.65 | Maximum | 13 | Municipal Manager | _Continous implementation of Project Plan | Chief Financial Officer | 2017-06-30
#REF! |  |  | Health Hazards (Solid waste dumping) | Illegal dumping |  | Critical | 5 | Common | 5 | Maximum | 25 | Usage of leased land | Unsatisfactory | 0.9 | Maximum | 22.5
Lists
|  | Impact | Likelihood | Control Design
|  | NA | NA | NA
|  | Critical | Common | Very good
|  | Major | Likely | Good
|  | Moderate | Moderate | Satisfactory
|  | Minor | Unlikely | Weak
|  | Insignificant | Rare | Unsatisfactory

## Workshop logistics
Bela-Bela Local Municipality
Risk Register
As at: 11 June 2018
Attendees: | Ngoepe NA | Manager | Limpopo Provincial Treasury
| Nkatingi MH | Manager | Limpopo Provincial Treasury
| Mothapo PJ | Acting ManagerSCOM | Bela-Bela Local Municipality
| Mothapo PJ | Acting CFO | Bela-Bela Local Municipality
| Moloto J | Div Head-Water | Bela-Bela Local Municipality
| Pilane T.R | Div Head-Roads | Bela-Bela Local Municipality
| Kabe MC | Div Head - Internal Audit | Bela-Bela Local Municipality
| Ramolobeng N | Div Head - HR | Bela-Bela Local Municipality
| Baartman V | Div Head - Expenditure | Bela-Bela Local Municipality
| Mohlala A | Div Head - Waste | Bela-Bela Local Municipality
| Magagane T.D | Chief Risk Officer | Bela-Bela Local Municipality
| Selatole V | Chief Accountant:Rates | Bela-Bela Local Municipality
| Maponya T.M | Electrical Engineer | Bela-Bela Local Municipality
| Mabotja K | IT Technician | Bela-Bela Local Municipality
| Mhlongo V | PMS Officer | Bela-Bela Local Municipality
| Mojela N | Intern | Bela-Bela Local Municipality
| Thobela P | Intern | Bela-Bela Local Municipality
| Mtshweni KP | Representative | Limpopo Provincial Treasury
| Sebotolo A.A | Representative | Limpopo Provincial Treasury
Venue: | Bela-Bela local Municipality Council Chambers

## Categories
Risk Register
As at: 11 June 2018
Factors used in Strategic Risk Analysis
Each risk is evaluated in terms of potential loss, likely hood of occurrence and the effectiveness of controls in place to manage the risks according to the criteria set out below
Potential Loss / Impact
Severity Ranking | Assessment
Critical | Negative outcomes or missed opportunities that are of critical importance to the achievement of objectives
5
Major | Negative outcomes or missed opportunities that are likely to have a relatively substantial impact on the ability to meet objectives
4
Moderate | Negative outcomes or missed opportunities that are likely to have a relatively moderate impact on the ability to meet objectives
3
Minor | Negative outcomes or missed opportunities that are likely to have a relatively low impact on the ability to meet objectives
2
Insignificant | Negative outcomes or missed opportunities that are likely to have a relatively negligible impact on the ability to meet objectives
1
Likelihood
Likelihood category | Category definition | Factor
Common | The risk is already occurring, or is likely to occur more than once within the next 12 months | 5
Likely | The risk could easily occur, and is likely to occur at least once within the next 12 months | 4
Moderate | There is an above average chance that the risk will occur at least once in the next three years | 3
Unlikely | The risk occurs infrequently and is unlikely to occur within the next three years | 2
Rare | The risk is conceivable but is only likely to occur in extreme circumstances | 1
Perceived control effectiveness and risk exposure at residual level
Effectiveness category | Category definition | Factor
Very good | Risk exposure is effectively controlled and managed | 20%
Good | Majority of risk exposure is effectively controlled and managed | 40%
Satisfactory | There is room for some improvement | 65%
Weak | Some of the risk exposure appears to be controlled, but there are major deficiencies | 80%
Unsatisfactory | Control measures are ineffective | 90%
Inherent risk exposure |  |  | Residual risk exposure
Inherent risk exposure | Factor |  | Residual risk exposure | Factor
Maximum | ³ 20 |  | Maximum | ³ 10
High | ³ 15 < 20 | 20 | High | ³ 7.5 < 10 | 10
Medium | ³ 10 < 15 | 15 | Medium | ³ 5 < 7.5 | 7.5
Low | ³ 5 < 10 | 10 | Low | ³ 2.5 < 5 | 5
Minimum | < 5 | 5 | Minimum | < 2.5 | 2.5

## Inherent vs Residual graph
Bela-Bela Local Municipality
#NAME?
As at: 11 June 2018
Note: Risk numbers refer to risks on risk register
Explanation: Risks shown on the left hand side are higher inherent risks. The greater the gap between the inherent and residual risk
the more effective the controls mitigating the risks are. Management should concentrate on controlling high inherent risks,
especially those with a low control effectiveness.
Note
The risk graph is automatically generated. Care should however be taken to ensure that the information recorded in the risk register has
been reflected in the risk graph. Should any additional rows be inserted or deleted care should be taken to ensure that the source data of the
graph reflects the actual rows needed to generate the graph. This is done by right clicking on the graph and selecting source data.
Once the source data screen comes up select series. You need to ensure that the values and category (X) axis labels reflects the correct rows
for both inherent and residual risk. To change from inherent risk to residual risk click on residual risk and the residual risk information will be reflected

## How to use
How to use this worksheet
1) | You type in the attendees / positions and venue
2) | You type in risk name, description and background
3) | Select the Impact (E), Likelihood (G) ratings
4) | Sort by the small column next to Inherent risk rating
5) | You type in current controls, actions, owners, timelines
6) | You select a Control effectiveness (L)
7) | You sort by the small column next to Residual risk.
8) | Check bar graph
11) | Print all sheets except for the "How to use" to have a complete report of the workshop