KPA 1:  Municipal Transformation and Organisational Development

| NO | PLANNED INTERVENTIONS | 2008/09 TARGETS | PROGRESS MADE BY 1st QUARTER | VARIANCES | KEY CHALLENGES |
| --- | --- | --- | --- | --- | --- |
| 1. Organisational Design and Human Resource Capacity |  |  |  |  |  |
| 1.2 | Filling of all vacant section 57 managers posts | Filling of all Section 57 vacancies | All Section 57 posts were filled | - | - |
| 1.3 | Signing of employment contracts by all Section 57 managers for the 2008/09 fy | All employment contracts of the Section 57 managers to be signed | All employment contracts of Section 57 managers have been signed | - | - |
| 1.4 | Review of the organogram of the municipality to ensure alignment with the IDP/ Budget | Aligning the 2008/ 09 organogram with the IDP and Budget. Recruitment. | The organogram was aligned to the IDP and Budget. There were no appointments made in the first quarter. | - | The Municipal Council placed a moratorium on all the vacant position in the first quarter which delayed recruitment. |
| 1.5 | Completion of the placement of staff in terms of Section 78 of the Municipal Systems Act (2000) | - | - | - | - |
| 2. Employment Equity |  |  |  |  |  |
| 2.1 | Employment Equity Plan in place | Completed Employment Equity Plan | Finalizing Employee Statistics | - | - |
| 2.2 | Number of Women representation in Section 57 Managers | 40% Women representation in Section 57 by 2011 | Currently there is 20% of Women representation in Section 57 | Fewer or no applications are received from skilled and experienced women. | Reviewing of the Employment equity plan and robust implementation of the plan |
| 2.3 | Total number of woman employed by the municipality against total staff | At least 40% of the municipal employees should be female by 2011 | The filling of the positions on the first on the last financial year catered for the appointment of female staff, as a result there was an increase from 22% (61) to 23% (64) in the number of municipal employees who are women. | Fewer or no applications are received from skilled and experienced women. | Reviewing of the Employment equity plan and robust implementation of the plan |
| 2.4 | Total number of disable staff in management level | At least 2% by 2011 | Currently there is no disabled staff in Management. | Fewer or no applications are received from skilled and experienced disabled. | Reviewing of the Employment equity plan and robust implementation of the plan |
| 3. Skills Development |  |  |  |  |  |
| 3.1 | Work Place Skills Development Plan submitted to LGSETA | Compilation of the plan and submission to LGSETA | Plan was compiled and submitted to LGSETA | - | - |
| 3.2 | Section 57 Managers development program | Training of 2 Section 57 managers (CPMD) | Currently attending the training. | - | - |
| 3.3 | Skill Levy Rebate | 76 officials to be trained | 44 officials have been trained | - | - |
| 4. Integrated Development Planning |  |  |  |  |  |
| 4.1 | Appointment of IDP officers | Appointment of the IDP Divisional Manager | The IDP Divisional Manager has been appointed | - | Staff shortages in the IDP and PMS Office. i.e. the office only has a Divisional Manager with no supporting staff. |
| 4.2 | 2008/09- 2012/13 IDP Approved | Obtaining approval for the 2008/ 09 IDP by May 2008 | The 2008/ 09 IDP was adopted on 29 May 2008. | - | - |
| 4.3 | Core sector plan included in the IDP (Spatial Development Framework , Disaster Management, MTIEF; Environmental Management Plans etc) | The inclusion of all sector plans on the 2008/ 09 IDP. | The 2008/09 IDP included all municipal (local and district) adopted sector and it also had the MTIEF. | - | - |
| 5. Functionality of the Performance Management System in compliance with Chapter of 6 of the MSA |  |  |  |  |  |
| 5.1 | Approved PMS policy and implementation framework in place | Preparation of the PMS Policy Framework and Engaging the DLGH: PMS Unit. | In – House Technical Research, Data collection and analysis. | - | - |
| 5.2 | Conducting of institutional performance review on periodic basis | Submission of the Monthly and Quarterly SDBIP performance reports to the municipal manager on the period basis and tabling to the all portfolio committees. | The Monthly and Quarterly SDBIP performance reports are submitted to the municipal manager on the period basis and tabled to the portfolio committees | - | - |
| 5.3 | Conducting of individual performance review on a periodic basis | Conducting the performance review of Section 57 Managers annually. | The performance review for 2007/ 08 has commenced and will be finalized in the second quarter. | - | - |
| 5.4 | Compliance with the Performance Regulation on Section 57 managers | Ensuring that the Performance Regulations are well adhered to. | The performance regulations are adhered to. | - | - |

KPA 2: Basic Service Delivery

| NO | PLANNED INTERVENTIONS | 2008/09 TARGETS | PROGRESS MADE BY 1st QUARTER | VARIANCES | KEY CHALLENGES |
| --- | --- | --- | --- | --- | --- |
| 1. Water Services |  |  |  |  |  |
| 1.1 | Free Basic Water Services | Provision of the free basic services to all the indigents who are registered with the municipal indigent list | Access to free basic water services is being provided to all the registered indigent households. | - | - |
| 1.2 | All communities have access to clean water and decent sanitation by 2010 | Ensuring that all households have access to decent water and sanitation by 2010 | All the households including the informal households are now provided with potable water in Bela Bela. There are approximately 450 HH which still lack decent sanitation in informal settlements and Rapotokwane | - | The households residing within Informal settlements are located in the areas that are not suitable for human habitation (i.e. floodplains, isolated private farms, land zoned for other uses such as Education). |
| 1.3 | Verification of municipal backlog | Eradication of all municipal back within the parameters that have been set by the IDP in line with millennium development goals and LG Strategic Agenda | - Water Backlogs = 0 HH - Sanitation Backlogs = 450 HH - Electricity Backlogs = 1000 HH - Refuse Backlogs = 571 HH | - | The households residing within Informal settlements are located in the areas that are not suitable for human habitation (i.e. floodplains, isolated private farms, land zoned for other uses such as Education). |
| 1.4 | Water and sanitation at all schools | All schools (30) to be serviced with water and sanitation. There must be no school built without these basic services. | - 29 schools have water. - 27 have sanitation. | - | - |
| 1.5 | Water and sanitation at all clinics | All clinics (3) to be serviced with water and sanitation. There must be no clinics built without basic services. | All three clinics have water and sanitation at the appropriate standard. | - | - |
| 1.6 | Reduction of unaccounted for water | Unaccounted to be reduced by from 20% to 5%. | Unaccounted for water has been reduced from 20% to 8.71% | - | - |
| 2. Electricity |  |  |  |  |  |
| 2.1 | Access to Free Basic Electricity | All indigent’s households to receive free basic electricity. | All registered Indigent households are benefiting from the free basic electricity. | - | - |
| 2.2 | New electricity connections | All new formal houses to be provided by electricity. | 50 new RDP houses | - | - |
| 2.3 | National Target : Electricity for all by 2012 | Eradication of the Electricity backlogs | The electricity backlog is currently estimated at 1000 Households | - | - |
| 3. Waste Removal |  |  |  |  |  |
| 3.1 | Waste Removal Policy | N/A | There is no strategy in place. | - | - |
| 3.2 | Waste Removal Strategy | N/A | There is no strategy in place. | - | - |
| 4. Roads and storm water |  |  |  |  |  |
| 4.1 | Roads Infrastructure Strategy | The preparation and implementation of the Infrastructure Capital Study. | The study has been completed and implementation has commenced. | - | - |
| 4.2 | New roads planned | Provision of new roads on in Bela Bela Township (Extension 8). | The contractor has been appointed and construction has commenced. | - | - |
| 4.3 | Maintenance and Rehabilitation of roads and storm water drainage | Maintaining all the roads and stormwater infrastructure that fall under the authority of Bela Bela Municipality. | Maintenance is undertaken on an on – going basis. i.e. all the reported potholes are patched. | - | - |
| 5. Indigent Policy Implementation Framework |  |  |  |  |  |
| 5.1 | Development of indigent policies in municipalities | Development and implementation of the indigent policy. | The policy was developed, adopted and it is currently being implemented to the benefits of all the indigents. | - | - |
| 5.2 | Development of indigent registers | Regular updates of the indigents register. | The indigent policy was updated on the on – going basis. | - | - |
| 6. Municipal Infrastructure Grant |  |  |  |  |  |
| 6.1 | Development of Municipal Infrastructure Investment Framework Strategy | Development of the Infrastructure maintenance plans. | In – progress | - | - |
| 6.2 | Development of Land Use Management Planning system | Development and Implementation of the Land Use Management Scheme | Municipal wide LUMS were developed and are currently being implemented. | - | - |
| 6.3 | Improving expenditure on MIG | 100% expenditure on MIG. Appointment of the PMU Technician. | The municipality achieved a 100% expenditure on MIG for 2007/ 08. The appointed candidate for PMU declined the offer. | - | - |
| 6.4 | Alignment of MIG with EPWP | N/A | No – Progress | - | Lack of EPWP understanding by the Technical Unit of the municipality. |
| 7. Municipal Housing Plan & strategy implementation |  |  |  |  |  |
| 7.1 | Municipal Housing Plan | Preparation of the Municipal Housing Plan and Mainstreaming it to the IDP. | The municipal housing plan was prepared and adopted. It is currently being mainstreamed to the 2009/ 10 IDP | - | - |
| 7.2 | Housing Beneficiary List | Compilation and updating of housing beneficiary list. | Regular updates were done. | - | - |

## KPA 3:  Local Economic Development

| NO | PLANNED INTERVENTIONS | 2008/09 TARGETS | PROGRESS MADE BY 1st QUARTER | VARIANCES | KEY CHALLENGES |
| --- | --- | --- | --- | --- | --- |
| 1. LED STRATEGY |  |  |  |  |  |
| 1.1 | Alignment of the District LED strategy with Local Municipalities LED Strategies | - Reviewing and Redeveloping the Local LED Strategy and aligning it with the District LED Strategy. | - The LED strategy has been reviewed and it is fully aligned to the District Strategy. | - | - |
| 1.2 | Alignment of LED Strategy with PGDS, EPWP, ASIGISA; PPP; NSDP; | Aligning the reviewed and redeveloped LED Strategy with PGDS, EPWP, ASGiSA, PPP and NSDP. | The LED strategy is now fully aligned to all the legislative imperatives. | - | - |
| 1.3 | Implementation of District LED Summit Action Plan | Active participation on Waterberg Summit Action Plan | Participated in Waterberg LED Road show. | - | - |
| 1.4 | Functionality of LED District Forum | N/A | N/A | - | - |
| 1.4 | LED units | Establishing the LED Unit and appointment of the LED Divisional Manager and LED Officer | No appointment made on the first quarter. | - | Moratorium was placed by Municipal Council on recruitment. |
| 1.5 | LED job creation initiatives | Promote the creation of jobs through LED initiatives and projects. | A total of 21 jobs were created through LED projects. | - | - |

KPA 4:  Municipal Financial Viability and Management:

| NO | PLANNED INTERVENTIONS | 2008/09 TARGETS | PROGRESS MADE BY 1st QUARTER | VARIANCES | KEY CHALLENGES |
| --- | --- | --- | --- | --- | --- |
| 1. MFMA Institutional compliance |  |  |  |  |  |
| 1.1 | Budget and Treasury Office | Setting up the Budget and Treasury Office and capacitating it. | The Budget and Treasury office is fully operational. There were few vacancies in the 1st due to resignation by some of the officials who occupied the critical positions. | - | The appointment was delayed due to moratorium. |
| 1.2 | MFMA implementation, monitoring and compliance plan | Preparation and implementation of all plans and mechanisms that are stipulated by MFMA (1) credit control and debt policy, (2) property rates policy, (3) indigent policy, (4) Budget, (5) SDBIP, (6) IDP and (7) Annual financial statements. | These policies/ plans and statements were prepared adopted and submitted to National and Provincial Treasury. | - | - |
| 1.3 | Audit Committee in place | Fully functional Audit Committee | Fully functional | - | - |
| 1.4 | Internal Audit Unit in place | Setting up the Internal Audit Unit and appointment of the Internal Auditor. | The Internal Auditor was appointed and the unit is fully functional. | - | The unit is however understaffed with only the Divisional Manager: Internal Audit being appointed. |
| 2. Implementation of financial systems, policies, and controls and regulations |  |  |  |  |  |
| 2.1 | Fraud Prevention and Anti Corruption mechanism and strategies | Development of a strategy to prevent fraud and corruption. | The Draft Fraud Prevention and Anti – corruption strategy and plans have been drafted. | - | - |
| 2.2 | Delegation of financial powers and functions | To have the delegation in place for financial powers and functions | In – place | - | - |
| 2.3 | Supply Chain Management policy | Development and implementation of the Supply Chain and Procurement Policy. | Developed and implemented. | - | - |
| 2.4 | BEE scorecards | To implement the BEE scorecards in terms of procurement of services. | Done in line with the requirements of the Supply Chain Management Policy | - | - |
| 2.5 | Credit Control and Debt Policy | Implementation of the credit control and debt policy. | The policy is being implemented. |  |  |
| 2.6 | Revenue collection strategies & targets for cost recovery | Implementation of the revenue collection strategies. | The strategies are being implemented. |  |  |
| 2.7 | Implementation of valuation rolls | Implementing the valuation roll. | Implementation undertaken. | - | There are objections on valuation by some properties and there are also properties which are not registered at the Deeds Office |
| 2.8 | Improvement of billing strategies and systems | Improving the billing strategies and systems. | Billing strategies have been improved and the system improvement are in – progress. | - | - |
| 2.9 | Compliance with accounting standards and systems | Full compliance with accounting standards and systems. | Conversion to GRAP/ GAMAP | - | - |
| 3. Budget and Expenditure Management |  |  |  |  |  |
| 3.1 | Preparation, and adoption of budget in compliance with MFMA | Preparation and adoption of the budget for 2008/ 09. | The budget plan was prepared and adopted. | - | - |
| 3.2 | Monthly and Quarterly Financial Reports | Preparation and submission of the monthly and quarterly financial reports on a regular basis. | All the monthly and quarterly reports were prepared and submitted. | - | - |
| 3.3 | Financial Statements | Preparation and submission of the annual financial statement for 2007/ 08 | The financial statements were prepared and submitted. | - | - |
| 3.4 | Implementation Plan to address audit reports of the Auditor General | Preparation and implementation of the plan. | The report back has not been received from the AG | - | - |

KPA 5:  Good Governance and Public Participation

| NO | PLANNED INTERVENTIONS | 2008/09 TARGETS | PROGRESS MADE BY 1st QUARTER | VARIANCES | KEY CHALLENGES |
| --- | --- | --- | --- | --- | --- |
| 1. Running of municipal council |  |  |  |  |  |
| 1.1 | Ordinary and special Council sitting | Undertaking of ordinary and special MC/ EC and Sub – committees | Done | - | - |
| 1.2 | Functionality of Mayoral committee & portfolio committee | Undertaking of Executive (EC) Committee and Portfolio Sub – Committees. | Fully Functional. | - | - |
| 1.3 | By-Laws, Policies and Strategy approval | Submission of policies, by – laws and strategies for approval by council | There was no bylaw passed for approval on the first quarter. | - | - |
| 1.4 | Conducting of by-laws in compliance with Municipal Electoral Act 2002 | Updating of by – laws. | In – progress | - | - |
| 2. Public Participation, Ward Committees |  |  |  |  |  |
| 2.1 | Establishment and Functionality of Wards committees | Ensuring that the ward committees are established, capacitated and fully functional. | Established and fully functional. | - | - |
| 2.2 | Budget and administrative support for ward committee | Provision of budget and administrative support to ward committees. | The budget and administrative support is being provided to support ward committees. | - | - |
| 2.3 | Ward IDP Plan | Ensuring that all ward committees and CDWs participate on the IDP process. | Done as part of 2008/ 09 IDP Review |  |  |
| 2.4 | Involvement of CDW | Involvement of CDW in the IDP, Imbizo and other public participation meetings | Done on the 2007/ 08 financial year. A total of 26 Public participation meetings were undertaken and the CDWs were involved. |  |  |
| 3. Corporate Governance |  |  |  |  |  |
| 3.1 Implementation of Communication Policies and Strategies |  |  |  |  |  |
| 3.1.1 | Communication Strategy | Preparation and implementation of the strategy | The Communication Strategy has been developed and adopted by Management. Implementation is ongoing | - | - |
| 3.1.2 | Communication unit | Setting up of the communication unit and capacitating it. | Communication Unit is fully functional. | - | - |
| 3.1.3 | Community satisfaction surveys | Displaying of the suggestion boxes and compiling the consolidated reports per quarter. | Suggestion boxes displayed. Report outstanding. | - | - |
| 3.1.4 | Functional complaint management systems | N/A | N/A | - | - |
| 3.2 | Municipal Information Technology | Establishing the Municipal Information technology | The IT unit was set up and the Divisional Manager: IT was appointed. There are plans to capacitate the unit with more staff. | - | - |
| 3.2.1 | Municipal Information Masters Systems Plan | Establishing Municipal Information Masters Systems Plan | The service provider was appointed by the District (WDM) and DLGH, has conducted an audit and will be submitting the report through which the recommendations will be drawn and implementation will begin. | - | - |
| 3.2.2 | Municipal website functional and updated | Updating the municipal website | Done | - | - |
| 3.2.3 | Provision of municipal services via electronic communication | N/A | N/A | - | - |
| 4. Fraud and Anti Corruption Implementation |  |  |  |  |  |
| 4.1 | District Fraud Prevention and Anti-Corruption Strategies and mechanism | N/A | N/A | - | - |