1.	INTRODUCTION	1

1.1	Purpose of this document	1

1.2	Bela Bela’s Vision, Mission and Values	1

1.3	Legal Framework for the SDBIP	1

1.4	The Service Delivery and Budget Implementation Concept	2

1.5	Top – Layer or Institutional SDBIP	2

1.6	Structure of this Report	2

2.	BELA – BELA 2008/ 09 SDBIP IN CONTEXT: TARGETS TO IMPLEMENT THE STRATEGIES SET BY THE REVISED IDP 2008/ 09	3

2.1	Office of the Municipal Manager	3

2.2	Technical Services	3

2.3	Planning and Economic Development	4

2.4	Social and Community Services	4

2.5	Budget and Treasury	4

2.6	Corporate Services	4

# 3. ANNEXURE A: REVENUE BY SOURCE

- Detailed Revenue Projections by Source

- Graphical Overview of Total Revenue

- Graphical Overview of Revenue by Source

# 4. ANNEXURE B: QUATERLY REVENUE AND EXPENDITURE PROJECTIONS BY VOTE

- Quarterly Summary of Projections of Revenue and Expenditure per Vote

- Monthly Summary of Projections of Revenue and Expenditure Per Vote:  July To December 2007

- Monthly Summary of Projections of Revenue and Expenditure Per Vote: January To June 2008

# 5. ANNEXURE C: CAPITAL WORKS PLAN

- Breakdown of Capital Funding by Source

- Breakdown of Capital Expenditure by Vote

# 6. ANNEXURE D: SERVICE DELIVERY TARGETS AND PERFORMANCE INDICATORS BY VOTE

- Office of the Municipal Manager

- Technical Services

- Planning and Economic Development

- Social and Economic Development

- Budget and Treasury

- Corporate Services

# INTRODUCTION

## Purpose of this document

This document presents the Draft Service Delivery and Budget Implementation Plan (SDBIP) for Bela – Bela’s 2008/ 09 financial year. It is a result of the consultative and participatory process involving all the management officials from Bela Bela Local Municipality. This report is intended to enable the Municipal Manager to monitor the performance of Senior Managers, the Mayor to monitor the performance of the Municipal Manager and the Community to monitor the performance of Bela Bela Local Municipality.

The SDBIP provides a vital link between the Mayor, Executive Council, administration and facilitates the process for holding the management accountable for its performance. Therefore this SDBIP report serves as a management, implementation and monitoring tool that is produced to assist Bela – Bela Local Municipality’s Mayor, Municipal Manager, Senior Managers and the Community on the ground.

## Bela Bela’s Vision, Mission and Values

The municipality’s has a long – term vision which has a strong emphasis on development and success of Bela – Bela Municipal Area. This vision can be re – called from the Revised Integrated Development Plan for 2008/ 09 and outlined as follows:-

“It is the vision of Bela – Bela Local Municipality to strive for the development of the municipality to be safe, prosperous and well maintained”

The mission and values which also appear on the IDP 2008/ 09 emphases that in order to achieve the above stated vision Bela Bela needs the:-

- Combined efforts of all residents of the municipality regardless of race, age and gender;

- Assistance of departments in the other two spheres of government; and

- Municipal council of Bela Bela as the driving force towards it all.

## Legal Framework for the SDBIP

The Service Delivery and Budget Implementation Plan is enforced by the law. The legal parameters that can be quoted in this case includes the specific sections of the Municipal Finance Management Act No. 56 of 2003 and these can be discussed as follows:-

- Section 69 (3)(a) – states that “the Accounting Officer must no later than 14 days after the approval of the annual budget submit to Mayor a draft SDBIP for the budget year”.

- Section 53 (1)(c)(ii) – states that “the Mayor must take all reasonable steps to ensure that the Municipality’s SDBIP is approved within 28 days after the approval of the budget”.

- Section 53 (3)(a) – states that “the Accounting Officer must ensure that the revenue and expenditure projections for each month and the service delivery and budget implementation plan, are made public no latter than 14 days after the approval of Service and Budget Implementation Plan.

## The Service Delivery and Budget Implementation Concept

The SDBIP contains information regarding service delivery targets, performance indicators, revenue and expenditure. The graph below is an indication of the elements that are directly linked to the SDBIP concept.

Figure 1: SDBIP Concept

SDBIP

Service delivery targets

Performance indicators

Revenue and Expenditure by vote

Council

Administration

IDP

Budget

Employees

Contracts and annual performance agreements for the Municipal Manager and Senior Managers

Monthly reports

Quarterly reports

Mid – Year Performance Assessment

Annual Report

It should be noted that the SDBIP is firstly informed by the IDP and Budget, secondly the annual performance agreements/ contracts of the Municipal Manager and Senior Managers must be influenced by the SDBIP and thirdly the in – year reporting (monthly and quarterly), and annual reporting on functional service delivery should be done against the information contained in the approved SDBIP.

## Top – Layer or Institutional SDBIP

As illustrated in figure 2 below the SDBIP is a top – layer or an institutional plan that is supported by a detailed Departmental Operational Plans or Departmental Scorecards which provides further information on how each Department will realize service delivery targets published in the top – layer SDBIP.

Figure 2: SDBIP as a Top – Layer or Institutional Plan

Published SDBIP

(Top Layer)

SDBIP

Supporting Documentation

## Structure of this Report

This report is divided into six sections in addition to this introduction. It is important for the reader to understand the purpose and content of each section. The following is therefore a brief overview of each section contained in this report:-

- Bela – Bela SDBIP in Context (Section 2) – is a brief contextual analysis which examine how Bela – Bela SDBIP targets for 2008/ 09 financial year will respond to the Revised IDP for 2008/ 09 strategies and priority issues. This is broken down per each department within the municipality.

- Annexure A (Revenue by Source) is a detailed indication of financial capacity (revenue) that is projected on a monthly basis for 2008/ 09 within Bela Bela Municipality.

- Annexure B (Quarterly Revenue and Expenditure projections by vote – is a summary of the projected revenue on a monthly and quarterly basis against the allocation for expenditure.

- Annexure C: Capital Works Plan – specify the budget that is allocated for capital projects and an indication of where the capital funds will be sourced. The tables and pie charts diagrams have been used to illustrate this.

- Annexure D: Service Delivery Targets and Performance Indicators by Vote – the targets that are made by each department (within the municipality) with regards to the services that they will deliver based on the available capacity and capability for 2008/ 09 financial year.

- Conclusion and a Way Forward – Monitoring and Reporting (Section 6) – is a brief discussion regarding the monitoring of the SDBIP implementation by the Municipal Manager through a series of reports submitted by the Senior Managers on a monthly, quarterly and annual basis as stipulated by the Municipal Finance Management Act No. 56 of 2003. This section therefore serves to be a brief conclusion and a way forward regarding the SDBIP for this financial year.

# BELA – BELA 2008/ 09 SDBIP IN CONTEXT: TARGETS TO IMPLEMENT THE STRATEGIES SET BY THE REVISED IDP 2008/ 09

## Office of the Municipal Manager

The Municipal Manager is the Head of the Administration within Bela Bela Municipality. The other functions performed by the office of the Municipal Manager are Communication and Internal Auditing. The operations of the Communication Division are in line with the principles of Good Governance which is priority number six (6) of the revised 2008/ 09 IDP. The communication division has therefore target to revise and implement the communication strategy for 2008/ 09 financial year, to develop the municipal newsletter, promote public participation, co-ordinate the internal and external imbizos, to improve the image of the municipality, update the municipal website, support the ward committees, CDWs, Councilors and to coordinate events, sports, art, culture and recreation and special programmes. The functions of the Internal Audit Division are in line with Municipal Transformation and Institutional Development which is priority eleven (11) of the revised 2008/ 09 IDP. In line with this priority the Internal Audit Division has targeted to conduct a number of audits, finalize the preparation of the Risk Management Strategy and Anti – Corruption Strategy and facilitate the implementation thereof.

## Technical Services

This first three priorities of the revised 2008/ 09 IDP are related to infrastructure development (Priority 1: Roads and Stormwater, Priority 2: Electricity and Priority 3: Water and Sanitation) and the Department of Technical Services is the custodian of infrastructure service delivery. In line with the revised 2008/ 09 IDP the Technical Services Department has set targets to implement the infrastructure capital projects that were identified on the revised IDP. To mention the few, these capital projects include the resealing of the roads in the CDB, Paving of access road in the township, upgrading of electrical network in Bela Bela Township and refurbishment of the Pumpstations.

## Planning and Economic Development

Land, Housing and Infrastructure Delivery is the fourth (4th) priority of revised 2008/ 09 IDP and this Department has targeted to coordinate housing development for low and middle income groups within Bela Bela, as well as to facilitate township establishment and to process applications for residential sites. Local Economic Development is the fifth (5th) priority as identified in the revised 2008/ 09 IDP. This department has therefore targeted to achieve a number of economic development aims. These include amongst others the promotion of tourism as the key driver for the local economy, SMME development and township based tourism, monitoring of economic growth and job creation. This Department also accommodates the IDP and PMS Division which is responsible for the overall development, management and facilitation of the Integrated Development Planning Process and Performance Management of the municipal institution. The IDP division has therefore identified all the functions and operations that it will undertake relating to IDP, PMS and Service Delivery Reporting and projected targets through which it intends to achieve these functions.

## Social and Community Services

The Social and Community Services Department has targeted maintain a number of community facilities including parks, cemeteries and sports fields to mention a few. In terms of the revised 2008/ 09 IDP, this Department has targeted to implement some of the capital projects which includes the provision of ablution facilities and fall under priority number seven (7) and other projects fall under Institutional Development which priority number eleven (11). This department if also responsible for Protection and Emergency Services, therefore there are targets which have been made regarding the operations of that Division.

## Budget and Treasury

This department is mainly responsible for budgeting, revenue management, expenditure management, implementation of the supply chain policy and financial reporting. Budget and Treasury has therefore made targets to deliver these services within this financial year and made projections with regards to the magnitude at which these services will be delivered.

## Corporate Services

The functions that this department has targeted to perform are in line with the 11th priority of the revised IDP (i.e. Municipal Transformation and Institutional Development) and these include Implementation of the Workplace Skills Plan, Organisational Arrangements and Development and Employment Equity Plan.